## Summary
QA Group Estimate :
| QA Activities | Effort (Man hours) | Comments/Remarks
Test case design Phase
| Existing application familiarization /Oritentation/KT for the team | 10
| Requirement Analysis | 5
| Test Plan / Test Strategy | 5
| Test Environment setup | 10
| Ad hoc testing | 10
Functional | Test case development including Peer review and updates | 30
| Test lead/Coordination/status reporting efforts | 7 | Industry standard 10%
| Total Design Efforts | 77
Execution
| Test execution (Cycle 1) | 40
| Defect logging (Cycle 1) | 1
| Test execution (Cycle 2) | 40
| Defect logging (Cycle 2) | 8
| Final defect round to meet exit criteria | 81 | Assumed 3 days approx for defect testing by 3 resources. Any pending open defects based on exit critieria and stability of the product
| Sub total Execution effort | 170
| Test lead/coordination effort | 17 | Industry standard 10%
| Total Execution Efforts | 187
| UAT | 40
| UAT Support | 10 | Interacting with End Users and supporting.
| Contingency factor 25% | 66 | since its highlevel and not full scope known on scenarios etc, Hence considered 25% as per TCOE process
| Post Production support | 100
| Training to support team | 30 | Exporting test cases from HP ALM to excel and preparing document on HP ALM.
| Total Efforts (hours) | 510
| Total Efforts in Man days | 63.75 | Assumed 9 hours/ day but actual productivity on testing excluding status calls, meetings, discussions, etc considered 8 hours/day
Other parameters considered
Show stopper defects with temporary fix using which continuation of test execution and the same need to be re tested when it arrives in the build.
Any Showstopper bugs need to be addressed immediately to the development team by simulating in front of the development team
Performing a smoke test for that feature once the next QC build arrives to ensure no critical bugs because of code change
At times, development team may need QC team to simulate the bug as it may not arise in development environment which needs additional effort
© www.SoftwareTestingHelp.com
Note on D19: rameshn: Provide your comments as: 1. How may test cases anticipated, data setup efforts if there are, complexities of test cases in numbers 2. Be ready for requirements traceability matrix which talks of test scenarios with complexities as shown in Sample Estimation details worksheet For Example: Total test cases anticipated: Total simple test cases; Total Medium Test cases: Total High test cases: Total Complex test cases: Total Exceptional test cases: